Monthly Sustainers - OHANA

Project Brief

Situation:

C.E.O. Women currently only has 3 recurring donors.  We believe there is potential to recruit more donors by running a recurring donor campaign that offers exclusive donors benefits.  This will help the organization create a more steady income stream.

Objectives:

To build a sustainable base of funding for C.E.O. Women by converting 100 people into recurring donors in 2011.

Target Audience:

Existing C.E.O. Women Donors

Online visitors to our website

People who attend house party events in 2011

Friends and family of staff and board, clients

Advisory Board Members

Corporate employees

Non-profit community members

Key Message:

OHANA Members are part of the C.E.O. Women family of supporters.  But unlike other supporters, OHANA Members commit to making a recurring, monthly contribution to C.E.O. Women.   Be one of our first 100 OHANA Members in 2011!

Supporting Points:

OHANA means “family” in Hawaiian.  OHANA Members are just that – part of the C.E.O. Women family and all that we stand for.  OHANA Members care about empowering women through entrepreneurship and supporting our local economy.  They directly support women owned businesses and enable ongoing training and support for countless other immigrant women from over 44 countries. In exchange for their on-going support, they receive locally produced, hand made goodies from our Burmese, Ethiopian and Mexican entrepreneurs!

Program Elements:

- Handcrafted gift made by local entrepreneur, received 8-12 weeks after they sign up for the program

- Personal letter from entrepreneur – To be received in April and November only, to coincide with cycles of our classes

- Card describing entrepreneur and her story for each gift

- Pictures of gifts and entrepreneurs

- OHANA Member Logo

- Thank you letter signed personally by President

- Reception event celebrating 100 OHANA Members with opportunity to meet entrepreneurs

- Quarterly special message to OHANA Members from the President updating them on the program

Sponsorship Opportunities:   Total Revenue Projections:

OHANA Members contributing $250 per month will receive a personal, hand written letter from a sponsored entrepreneur, alfajores, a handmade trivet, a handmade silk scarf and will be listed on our website as our first 100 OHANA Members.

OHANA Members contributing $100 per month will receive a personal, hand written letter from a sponsored entrepreneur, and a choice of alfajores, a handmade trivet, or a handmade silk scarf.  They will be listed on our website as our first 100 OHANA Members.

OHANA Members contributing $50 per month will receive a delicious bag of alfajores (Peruvian shortbread cookies) handmade by food entrepreneur Heeidy Pascarello of Manos Latinas catering.

OHANA Members contributing $25 per month will receive a handmade trivet by one of our Ethiopian entrepreneurs and will be listed on our website as our first 100 OHANA Members.

All OHANA Members contributing $10 monthly will receive a silk scarf, hand woven by a Burmese refugee women’s weaving collective and will be listed on our website as our first 100 OHANA Members.

When have 100 OHANA Members, we’ll invite everyone over to our offices for a “tropical” reception with locally produced food and desserts catered by our entrepreneurs plus drinks and world music!  We can’t wait to make you part of the family!

Public Relations:

All OHANA Members will be listed on our website, annual report and in materials associated with the campaign.

Project Team:

X,y,z

Assembling Inventory, Fulfillment and Mailing of gifts: Name

Client Story Assembly, Thank you Letter, Photography/ layout, Online set up: Name

Reception: All

Approval:   x

Timeline:

Responsibility		Task						Date	______

Name			Concept Delivered and finalized

Name			Budget Complete

Name			Logo and Picture Assets Developed

Name			Logo and Picture Assets Approval

Name			Mention in Feb enews

Name			Campaign  e-mail copy developed

Name			Campaign e-mail copy approval

Name			Client Stories Completed

Name			Website donate now page updated

Name			Campaign Launch e-mail/ website

Name			Fulfillment

Revenue:

|  | Mar | Apr | May | June | Jul | Aug | Sept | Oct | Nov | Dec |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| $10/mo | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 |
| $25/mo | 1 | 1 | 2 | 2 | 3 | 3 | 4 | 5 | 6 | 7 |
| $50/mo |  | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 4 | 4 |
| $100/mo |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 |
| Total $ | $45 | $115 | $260 | $280 | $375 | $395 | $440 | $535 | $730 | $775 |

Total: $3,950 for 33 donors

Estimate: $11,850 for 99 donors in 2011

Budget:

Estimated cost for products, packaging, and postage:

| Nwe’s scarves | $10/each | Estimated: 22 | $ 220.00 |
| --- | --- | --- | --- |
| Postage for scarves | $2.07/each |  | $ 45.54 |
| Winou’s trivets | $15/each | Estimated: 9 | $ 135.00 |
| Postage for trivets | $1.39/each |  | $ 12.51 |
| Heeidy’s alfajores | $13/each (12 count) | Estimated: 6 | $ 78.00 |
| Manila envelopes |  |  | $ 5.60 |
| Tissue paper |  |  | $ 3.16 |
| 5” square boxes | Uline S-4050 |  | $ 6.25 |
| Bubble wrap | Uline S-3927P |  | $ 39.00 |
| Shipping for Uline |  |  | $ 10.00 |
| Travel for alfajores | 25-35 miles | $0.51/mile; 6 trips | $ 214.20 |
| BART travel for trivets | 9 trips | $3.50 round trip | $ 31.50 |
|  |  | TOTAL | $ 800.76 |

Estimated staff time:

| TASK | NOTES | TIME |
| --- | --- | --- |
| Research and procure sample products; assess postage and packaging | Name | 2 hours |
| Strategy and branding planning | Name | 6 hours |
| Logo design | Name | 6 hours |
| Photograph products; edit photos | Name | 2 hours |
| Write text for product cards | Name | 3 hours |
| Edit/proof text for product cards | Name | 2 hours |
| Get estimates for printing cards; arrange for printing | Name | 2 hours |
| Tie orange ribbons to product cards | Name | 2 hours |
| Website infrastructure | Name | 5 hours |
| Package & mail products | 10 mins each/36 packages (R) | 22 hours |
| Trips to Livermore | 60 minutes each/6 trips (R) | 6 hours |
| Trips to MacArthur | 60 minutes each/9 trips (R) | 9 hours |
| Schmoozing with clients | 15 minutes each/28 (R) | 7 hours |
| New donor set up; thank yous | 30 minutes each/28 donors (M) | 14 hours |
| OHANA Communications | Name; two hours/quarter | 8 hours |
|  | TOTAL | 96 hours |
| Rachel’s time cost (88 hours) * ($22.60/hour+15%) |  | $2,290.00 |

Cost to make a $1.00 - $.26